|  | Hengyi Industries Sdn Bhd 恒逸实业（文莱）有限公司 |  |  |
| --- | --- | --- | --- |
|  | Dispatcher Daily Report 调运日报 |  |  |
| Establishment Department 编制部门 |  | Commercial Department 商务部 | April 28, 2019 |

Weather Forecast

天气预测

| 28 April-4 May |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Weather天气 | Rain 雨 | Rain 雨 | Rain 雨 | Rain 雨 | Rain 雨 | sunny 晴 | Sunny 晴 |
| Wind Power 风力 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 |

Arrival Schedule of Ships

船舶到港计划表

| Name of goods 货名 | Name of vessel 船名 | Loading (Unloading) Berth 装（卸）船泊位 | Loading (Unloading) Capacity 装（卸）船量 | Pre Arrival Period 预到港期 |
| --- | --- | --- | --- | --- |
| SERIA | MV NordSymphony | SPM | 80000 | 24/Apr |
| Coal | MV Pos Oceania | 8# | 22000 | 1/May |
| Refined Naphtha | MV EAGLE MILAN | 4# L401 | 38000 | 12/May |
| Remarks 备注 | MV NordSymphony4月24日已到锚地等待卸港。 |  |  |  |

Statistics of Outsourcing Raw Materials (Unit: Tons)

外购原料统计（单位：吨）

| Product Number 品号 | Incoming Volume 进厂量 | Usage Quantity 使用量 | Stock 库存 | Turnover Days 可周转天数 |
| --- | --- | --- | --- | --- |
| Crude Oil 原油 | - | - | 0 | 0 |
| Coal煤炭 | 0 | 520 | 35584 | 24 |
| Catalytic Gasoline 催化汽油 | - | - | 0 | 0 |
| Heavy Naphtha 重石脑油 | - | - | 0 | 0 |
| Diesel Power Station 电站柴油 | 0 | - | 70 | - |
| Note注：24日拖轮Rohana加油60000 L On the 24th, tugboat Rohana refueled 60,000 L |  |  |  |  |

Statistical Analysis of Equipment Products (Unit: Tons)

装置产品统计（单位：吨）

| Product Number 品号 | yield 产量 | Sales volume 销售量 | Stock 库存 | Saleable Inventory 可销售库存 | Turnover Days 可周转天数 |
| --- | --- | --- | --- | --- | --- |
| Ash 粉煤灰 | 25 | 0 | 380 | 300 | 4 |

Production and Equipment Abnormal Problem Tracking: (In the dispatching log, only the equipment abnormal situation affecting the sales of wharf and loading station is tracked and recorded) .                        生产及设备异常问题跟踪：（调度日志中仅对码头、装车站影响销售的设备异常情况进行跟踪记录）

| Department 部门 | Abnormal Production and Equipment Problems 生产及设备异常问题 |
| --- | --- |
| Wharf 码头 | 施工、报审中Construction and report are in progress |
| Loading Station 装车站 | 建设施工中Under construction |

Existing Problems                                                                                    存在问题

- Thailand's Mixed Fang Bidding Letter for the Loading Period was issued in late May. The Loading Period is 22-24 May. Singapore is ready to bid. Check with Japanese suppliers about the possibility of supply. Japanese suppliers were out of stock in May. They were asked to check the feasibility of the end of May for a response. According to the actual progress of the project and the government's permission, mixed aromatic hydrocarbons can enter the plant in late June.                                                                                                   泰国混芳5月下旬装期招标书已发出，装期5月22-24日，新加坡准备去投标。跟日本供应商查看供货的可能性，日本供应商五月份没货。要求他们查看5月底的可行性，待回复。根据目前工程实际进度以及政府许可情况看，混合芳烃可以6月下旬进厂。

- The overseas agent company is our bottled LPG supplier.Due to the current torch construction schedule and site, the arrival time has been delayed. The specific time will be notified one week in advance..                                                                                  确定Overseas Agency Company海外代理公司为我司瓶装液化气供应商。目前火炬施工进度及场地等原因，进厂时间推迟，具体时间计调部提前一周通知。

- The fourth coal ship "MV Pos Oceania" arrived at the loading port Tanjung Bara Anchorage in the early morning of April 19, and has docked at the port of loading on April 26. Currently, ETA is at PM on May 1。                                                                     第四船煤炭船舶“MV Pos Oceania”4月19日凌晨到达装货港Tanjung Bara Anchorage，26日靠泊装港装货，ETA 5月1日PM。

- The purchase plan of the fifth ship's coal planning and regulation department requires 35,000 tons of purchasing volume, and the arrival date is in the first ten days of May. Due to the Eastern Waterway Drainage Restriction, Singaporean companies and suppliers delayed their talks until May 10.                                                                             第五船煤炭计调部采购计划单要求采购量3.5万吨，到港期5月上旬；因东航道吃水限制问题，新加坡公司和供应商商谈推迟到港期至5月10日之后。

- The First Ship of SERIA Crude Oil "MV Nord Symphony", arrived at Port Pulau Muara Besa at 6:00 on April 24, and is still at anchorage. It will berth and unload at the port when the terminal has the conditions for receiving and unloading.                                                                       首船诗里亚原油“MV NordSymphony” 于4月24日6:00抵达Port Pulau Muara Besa，目前仍在锚地，待码头具备接卸条件后进行靠泊卸港作业。

- The liquefied petroleum gas (LPG) from the first vessel is still in the inquiry as planned. Due to the uncertainty of the refinery, the delivery date will be later than May 30.                                                                                                          首船开工液化气仍按照计划要求对外询盘中， 由于炼厂还未确定，到货期会晚于5月30日。

Compiling person 编制人：张 拓                      Auditor 审核人：谭斌