|  | Hengyi Industries Sdn Bhd 恒逸实业（文莱）有限公司 |  |  |
| --- | --- | --- | --- |
|  | Dispatcher Daily Report 调运日报 |  |  |
| Establishment Department 编制部门 |  | Commercial Department 商务部 | 10 September 2019 |

Weather Forecast

天气预测

| 10 September -16 September |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Weather天气 | Rain 雨 | Sunny 晴 | Rain 雨 | Sunny 晴 | Rain 雨 | Rain 雨 | Sunny 晴 |
| Wind Power 风力 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 |

Arrival Schedule of Ships

船舶到港计划表

| Name of goods 货名 | Name of vessel 船名 | Loading (Unloading) Berth 装（卸）船泊位 | Loading (Unloading) Capacity 装（卸）船量(吨) | Pre Arrival Period 预到港期 |
| --- | --- | --- | --- | --- |
| 9月下旬煤炭 | MV MAPLE GLORY | 8# | 32000 | 9月16日-20日 |
| 10月上旬煤炭 | - | 8# | - | - |
| 10月中旬煤炭 | - | 8# | - | - |
| Zakum原油 | MT COSWISDOM | 单点 | 130000 | 10月8日-10日 |
| CPC原油 |  | 单点 | 130000 |  |
| kimanis原油 |  | 单点 | 80000 |  |
| QATAR MARINE 原油 |  | 单点 | 130000 |  |
| SERIA原油 |  | 单点 | 80000 |  |
| MURBAN原油 |  | 单点 | 130000 |  |
| QATAR MARINE 原油 |  | 单点 | 130000 |  |
| Remarks 备注 |  |  |  |  |

Statistics of Outsourcing Raw Materials (Unit: Tons)

外购原料统计（单位：吨）

| Product Number 品号 | Incoming Volume进厂量（卸货港商检量） | Usage Quantity 使用量 | Stock 当日库存 | Turnover Days 可周转天数 |
| --- | --- | --- | --- | --- |
| Crude Oil 原油 | 567973.673（12/5船） | 14863 | 550479 | - |
| Coal煤炭 | 233000（12/9船） | 1163 | 57999 | 49 |
| Catalytic Gasoline 汽油组分 | 19868.626（1/1船） | - | 19923 | - |
| Heavy Naphtha 重石脑油 | 19508.401（1/1船） | - | 19829 | - |
| Refined naphtha精制石脑油 | 37977.623（1/1船） | - | 38341 | - |
| Mixed Aromatics 混合芳烃 | 14787.911（1/1船） | - | 15425 | - |
| Mixed xylene混合二甲苯 | 14245.938（2/2船） | - | 8058 | - |
| LPG液化石油气 | 10066.830（4/4船） | 183 | 7873 | - |
| Diesel开工柴油 | 9874.735（2/2船） | - | 6681 | - |
| Remarks备注： It plans to purchase 9 kinds of 30 kinds of materials (including 12 ships of coal, 9 ships have arrived, and 18 ships have started to supply 17 kinds of raw materials). 计划采购物料9种36船（包含12船煤炭已到港9船，24船开工原料油已到港17船），其中 1.The start of the raw material oil project plans to purchase 8 kinds of 18 ships, and 8 types of 17 ships have been delivered to the port for a total of 694,300.459 tons of unloading goods to the port, There are 130,000 tons of Zakum crude oil on the 1st ship of October and 680,000 tons of crude oil on the 6th ship of November; 1、开工原料油计划采购8种24船，已到港完成卸货8种17船共计卸货量694300.459吨，剩余未到港10月1船Zakum原油13万吨，11月6船原油68万吨； 2. Currently, 12 ships are planned to be purchased for coal production materials. 9 ships have landed at the port and discharged 233,400 tons, while 3 ships haven't arrived at the port for 122,000 tons. The coal that has not arrived at the port is respectively: 32,000 tons per ship in late September, 45,000 tons each arriving at the port from October 1st to 5th and October 20th; 2、生产物料煤炭目前计划采购12船，已到港卸货9船23.34万吨，3船未到港12.2万吨， 未到港煤炭分别为： 9月下旬1船3.2万吨，10月1日-5日、10月20日前各到港1船4.5万吨； |  |  |  |  |

Atmospheric decompression

常减压开工情况

| 项目 |  | 数据 t/h | 项目 |  | 数量 t/h | 原油库存 t |
| --- | --- | --- | --- | --- | --- | --- |
| 原油计划加工量 |  | 650 | 实际加工量 |  | 635 | 550479 |
| 产品名称 |  | 数量t/h | 当日数量t/d | 物料去向 |  | 产品库存 |
| 1 | 初顶油 | 80 | 1920 | 退轻污油至原油罐4002-T007 |  | - |
| 2 | 常顶油 | 57 | 1368 | 退轻污油至原油罐4002-T007 |  | - |
| 3 | 常一线 | 32 | 768 | 至直馏柴油产品线进4101-T006 |  | 5196 |
| 4 | 常二线 | 102 | 2448 | 并混合柴油出装置4101-T008 |  | 9175 |
| 5 | 常三线（并混合柴油） | 96 | 2304 | 并混合柴油出装置4101-T008 |  | - |
|  | 常三线（并减压蜡油） | / | / | 至加氢裂化原料4103-T003 |  | 8871 |
| 6 | 混合柴油 | 198 | 4752 | 常二线走混合柴油线上进4101-T008 |  | 9175 |
| 7 | 直馏蜡油 | 157 | 3768 | 加氢裂化原料罐 4103-T004 |  | 13810 |
| 8 | 减渣 | 111 | 2664 | 至焦化原料4103-T001 |  | 8044 |
| 9 | 轻污油 | - | - | 至4210-T003/4 |  | 619 |
| 10 | 重污油 | - | - | 至4211-T005/6 |  | 1625 |

Statistical Analysis of Equipment Products (Unit: Tons)

装置产品统计（单位：吨）

| Product Number 品号 | yield 产量 | Sales volume 销售量 | Stock 库存 | Saleable Inventory 可销售库存 |
| --- | --- | --- | --- | --- |
| Ash 粉煤灰 | 75 | 34.63 | 250 | 200 |

Production and Equipment Abnormal Problem Tracking: (In the dispatching log, only the equipment abnormal situation affecting the sales of wharf and loading station is tracked and recorded) .

生产及设备异常问题跟踪：（调度日志中仅对码头、装车站影响销售的设备异常情况进行跟踪记录）

| Department 部门 | Abnormal Production and Equipment Problems 生产及设备异常问题 |
| --- | --- |
| Wharf 码头 | 1、施工、报审中Construction and report are in progress； 2、煤码头长期LTO有效期到8月6号2020年 Long-term LTO for coal Jetty until 6/8/2020； |
| Loading Station 装车站 | 公路出厂设备及仪表部分已完成安装，调试在9月底能够完成，天梯系统与ERP联桥部分系统开发正在进行，预计在9月中旬可以进行调试 Gantry equipment and instruments have been installed, commissioning can be completed by the end of September, and the development of elevator system and ERP bridge system is under way. It is expected that commissioning can be carried out in mid-September. |

Logistics dispatch information

物流调运信息（9月10日06:00）

| 一、库存信息： |  |
| --- | --- |
| 1 | 1、 At 06AM on the 10th, the coal inventory was 57999 tons，yestoday consumed 1163 tons; 截止9月10日06:00，煤炭库存57999吨，昨日消耗1163吨； |
| 2 | At 06PM on the 9thThe ash warehouse stocks 210 tons. Today, RMX plans to haul 2 trucks with 22.66 tons and VSL haul 1 truck with 11.97 tons. Tomorrow, we plan to transport 1 truck for BHC and 1 truck for RMX; 截止9日18:00，灰库库存210吨，今日RMX计划拉运2车22.66吨，VSL拉运1车11.97吨； 明日计划BHC拉运1车，RMX拉运1车； |

| 二、船讯信息： |  |
| --- | --- |
| 1 | 1. In late September, the MV MAPLE GLORY coal ship has arrived at the loading port of Tanjung Bara, Indonesia. The pre-loading date is September 12, and the pre-arrival time to PMB is September 16 to 20; 9月下旬煤炭船MV MAPLE GLORY已抵达装货港印尼Tanjung Bara,预装期9月12日，预到PMB时间为9月16日到20日； |
| 2 | .ZAKUM crude oil tanker MT COSWISDOM in early October, pre-loading period September 15-17, loading port Zirku Petroleum Port, 1 million barrels; first to Singapore unloading quantity 130000 tons, then to PMB unloading quantity 130000 tons, is expected to arrive in PMB on October 8-10. 10月上旬ZAKUM原油船“MT COSWISDOM”,预装期9月15日-17日，装港Zirku Petroleum Port，货量100万桶；先到新加坡卸货13万吨，然后到PMB卸货13万吨，预计10月8日-10日抵达PMB。 |

Compiling person 编制人：王志锋                 Auditor 审核人：谢振林