|  | 恒逸实业（文莱）有限公司 Hengyi Industries Sdn Bhd |  |  |
| --- | --- | --- | --- |
|  | 商务调运日报 Dispatcher Daily Report |  |  |
| Establishment Department 编制部门 |  | Commercial Department 商务部 | 24 September 2019 |

Weather Forecast     天气预测

| 24September -27 September |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Weather天气 | Fog雾 | Rain 雨 | Sunny 晴 | Rain 雨 | Sunny 晴 | Rain 雨 | Rain 雨 |
| Wind Power 风力 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 |

Arrival Schedule of Ships   船舶到港计划表

| Classification 类别 | Name of goods 名称 | Name of vessel 船名 | Loading (Unloading) Berth装（卸）船泊位 | Loading (Unloading) Capacity装（卸）船量(吨) | Pre Arrival Period 预到港期 |
| --- | --- | --- | --- | --- | --- |
| 煤炭 | 10月上旬煤炭 | - | 8# | 45000 | 计划10月13-17日 |
|  | 10月中旬煤炭 | - | 8# | 45000 | 计划10月30-11月3日 |
|  | 11月中旬煤炭 |  | 8# | 45000 | 计划11月中旬 |
| 原油 | Zakum原油 | MT COSWISDOM | 单点 | 130000 | 10月5日1000LT |
|  | Saharn Blend 原油 |  | 单点 | 50000 | 计划10月30日 |
|  | CPC原油 |  | 单点 | 130000 | 11月1日-6日 |
|  | QATAR MARINE原油 |  | 单点 | 130000 | 11月2日-9日 |
|  | SERIA原油 |  | 单点 | 80000 | 11月3日-9日 |
|  | MURBAN原油 |  | 单点 | 130000 | 计划11月下旬 |
| 石脑油 | 11月重石脑油 |  | 4# | 35000 | 原计划11月20日，9月16日接计调部调整至12月5日-10日 |
| 催化汽油 | 11月催化汽油 |  | 4# | 35000 | 原计划11月20日，9月16日接计调部调整至11月25日-30日 |
| 液化气 | 10月液化气 |  | 4# | 2500 | 计划10月5日前 |
| Remarks 备注 | 电站计划9月下旬停工检修，检修时间为9月23日至30日约1周。10月2船煤炭分别调整至10月13-17日和10月30-11月3日到厂。 |  |  |  |  |

Statistics of Outsourcing Raw Materials (Unit: Tons)

外购原料统计（单位：吨）

| Product Number品号 | Incoming Volume进厂量 （卸货港商检量） | Usage Quantity 使用量 | Stock 当日库存 | Turnover Days 可周转天数 |
| --- | --- | --- | --- | --- |
| Crude Oil 原油 | 567973.673（11/5船） | - | 493798 | - |
| Coal煤炭 | 233000（13/10船） | - | 72248 | 23日停车，计划9月29日再开车 |
| Catalytic Gasoline 汽油组分 | 19868.626（2/1船） | - | 19923 | - |
| Heavy Naphtha 重石脑油 | 19508.401（2/1船） | - | 19829 | - |
| Refined naphtha精制石脑油 | 37977.623（1/1船） | - | 38341 | - |
| Mixed Aromatics 混合芳烃 | 14787.911（1/1船） | - | 15425 | - |
| Mixed xylene混合二甲苯 | 14245.938（2/2船） | - | 8058 | - |
| LPG液化石油气 | 10066.830（5/4船） | 26 | 5618 | - |
| Diesel开工柴油 | 9874.735（2/2船） | - | 6681 | - |
| Remarks备注： 计划采购物料9种39船（包含13船煤炭已到港9船，26船开工原料油已到港17船），其中 39 ships of 9 kinds of materials are planned to be purchased (including 9 ships of 13 ships of coal that have arrived at the port, and 17 ships of 26 ships of raw materials and oil that have started work that have arrived at the port). The details are as follows: 1、开工原料油计划采购8种26船，已到港完成卸货8种17船(表中蓝底色标注)共计卸货量694300.459吨，剩余未到港4种9船次；分别为：10月1船Zakum原油13万吨计划10月8日-10日到港，10月新增1船5万吨Saharn Blend 原油； 10月1船液化气0.25万吨计划10月5日到港；11月4船原油47万吨，1船催化汽油3.5万吨；12月1船重石脑油3.5万吨； 26 ships of 8 kinds of raw oil are planned to be purchased. 17 ships of 8 kinds of oil have completed unloading at the port of arrival (marked with blue background in the table). The total unloading volume is 694300.459 tons.They are: on October 1st, 130,000 tons of Zakum crude oil are scheduled to arrive at the port from October 8th to October 10th; on October 1st, 0.25 million tons of liquefied gas are scheduled to arrive at the port on October 5th;November 5 ship crude oil 550,000 tons;One ship catalyzed 35,000 tons of gasoline;December 1 ship weight naphtha 35,000 tons; 2、生产物料煤炭目前计划采购13船，已到港完成卸货10船26.54万吨，3船未到港13.5万吨；未到港煤炭分别为： 10月13日-17日、10月30日-11月3日前各到港1船各4.5万吨，11月中旬1船4.5万吨； Currently, 13 ships are planned to be purchased for coal production materials, 9 ships have already landed and discharged 233,400 tons, 4 ships have not arrived at the port for 167,000 tons, respectively: one ship has arrived at the port for 32,000 tons in late September, and the power station plans to overhaul on September 23 solstice 30.The original plan was to import 45,000 tons of coal into the plant from October 5th to October 10th, which was adjusted to October 13th to 17th.The original plan was to import 45,000 tons of coal into the plant on October 20, which was adjusted to October 30-november 3.45000 tons per ship in mid-november; |  |  |  |  |

Statistics of fly ash products (Unit: Tons)

粉煤灰产品统计（单位：吨）

| Product Number 品号 | Stock 库存（t） | yield 产量（t） | Daily sales 昨日销售量(t/车) | Weekly sales 本周销售(t/车) | Month sales 本月销售量(t/车) | Saleable Inventory 可销售库存（t） |
| --- | --- | --- | --- | --- | --- | --- |
| Ash 粉煤灰 | 202 | 0 | 57.15/5 | 57.15/5 | 512.69/47 | 202 |

生产及设备异常问题跟踪：（调度日志中仅对码头、装车站影响销售的设备异常情况进行跟踪记录）

| Department 部门 | Abnormal Production and Equipment Problems 生产及设备异常问题 |
| --- | --- |
| Wharf 码头 | 1、施工、报审中；Construction and report are in progress 2、煤码头长期LTO有效期到2020年8月6日；Long-term LTO for coal Jetty until 6/8/2020 3、煤码头升级批准预计9月中旬可以拿到，之后可靠泊载货吨不超5万吨的船型；The coal terminal upgrade approval is expected to be available in mid-September, and then the ship type with a reliable parking capacity of not more than 50,000 tons； |
| Loading Station 装车站 | Gantry equipment and instruments have been installed, commissioning can be completed by the end of September, and the development of elevator system and ERP bridge system is under way. 公路出厂设备及仪表部分已完成安装，调试在9月底能够完成，天梯系统与ERP联桥部分系统开发正在进行； |
| 备注：Production and Equipment Abnormal Problem Tracking: (In the dispatching log, only the equipment abnormal situation affecting the sales of wharf and loading station is tracked and recorded) . |  |

Logistics dispatch information库存及船讯（9月24日06:00）

| 一、库存信息： |  |
| --- | --- |
| 1 | 截止9月24日06:00，煤炭库存72243吨， 9月23日-9月29日期间，热电部停车检修，暂无煤炭消耗； As of 06:00 on September 24rd, coal inventory was 72,243 tons, From September 23rd to September 29th, the thermoelectric department stopped for maintenance, and there was no coal consumption temporarily. |
| 2 | 截止9月24日06:00，灰库库存212吨，昨日BHC拉运4车47.47吨，RMC拉运1车9.68吨；今日计划BHC拉运1车； As of 06:00, September 24, 212 tons of grey warehouse inventory,yesterday 47.47tons of 4 trucks transported by BHC and 9.68 tons of 1 truck transported by RMC.Today plan to transport 1 truck by BHC; |
| 二、船讯信息： |  |
| 1 | 9月下旬煤炭自9月20日到港，并于1525LT开始卸货，现已经于9月23日1100LT完成卸货，并于1510LT离港； 本次卸船累计用时65.5小时，在港总时间为73.5小时，卸货平均速率492吨/小时，未产生滞期，速遣时间为30.5小时,速遣费为6036$. In late September, the coal arrived at the port on September 20th and started unloading at 1525LT. Now, the unloading has been completed at 1100LT on September 23rd and left the port at 1510LT.The total unloading time was 65.5 hours, and the total time at the port was 73.5 hours. The average unloading rate was 492 tons/hour, without any demurrage. Dispatch time is 30.5 hours |
| 2 | 10月上旬ZAKUM原油船“MT COSWISDOM”于9月18日完成装货，装货量共计26万吨（200万桶），并于9月18日1000LT离开装货港驶往第一卸货港“新加坡”，预计9月30日抵达第一卸货港新加坡，卸货量13万吨（100万桶），然后再驶往PMB卸货，卸货量13万吨（100万桶），预计抵达PMB时间为10月5日1000LT； In early October ZAKUM oil ship "MT COSWISDOM" on September 18 complete loading, the loading quantity is 260000 tons (2 million barrels), and on September 18, 1000 lt from loading port to the first port of discharge "Singapore", September 30, is expected to arrive at the port of discharge in Singapore, the amount of discharge 130000 tons (1 million barrels), and then to PMB, discharge amount of discharge 130000 tons (1 million barrels), is expected to arrive in PMB for October 5 at 1000LT |
| 三、计划调整： |  |
| 1 | 9月16日接计调部计划调整通知，对11月部分原料进厂计划进行调整，具体如下：1、原定计划11月23日到1船QATAR MARINE原油，现此船计划取消；2、汽油调和组分原计划11月20日到，调整至11月25日-30日；3、石脑油原计划11月20日到，调整至12月5日-10日；4、9月21日接通知，10月新增1船5万吨Saharn Blend 原油，计划到港期10月30日； On September 16 (today), following the adjustment notice of the plan of the planning and research department, some raw materials in the factory in November were adjusted as follows: 1. QATAR MARINE crude oil was scheduled to arrive at the port on November 6, but the ship plan was cancelled; 2. Gasoline blending components were originally scheduled to arrive on November 20, but will be adjusted to November 25-30;3. Naphtha was originally scheduled to arrive on November 20, but was adjusted to December 5-10; 4、On September 21, notifications, add 1 October 50000 tons ship Saharn Blend oil, plans to Hong Kong on October 30; |
| 2 | 电站计划9月下旬停工检修，检修时间为9月23日至30日约1周。原计划10月5-10日进厂煤炭4.5万吨，调整至10月13-17日；原计划10月20日进厂煤炭4.5万吨，调整至10月30-11月3日，调整计划已于9月13日得到新加坡回复确认调整。 The power station is scheduled to stop maintenance in late September, and the maintenance time will be about 1 week on September 23 solstice 30.The original plan was to import 45,000 tons of coal into the plant from October 5th to October 10th, which was adjusted to October 13th to 17th.The original plan was to import 45,000 tons of coal into the plant on October 20, which was adjusted from October 30 to November 3. The adjustment plan was confirmed by Singapore on September 13. |