|  | 恒逸实业（文莱）有限公司 Hengyi Industries Sdn Bhd |  |  |
| --- | --- | --- | --- |
|  | 商务调运日报 Dispatcher Daily Report |  |  |
| Establishment Department 编制部门 |  | Commercial Department 商务部 | 7 October 2019 |

Weather Forecast     天气预测

| 6 October -12 October |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Weather天气 | Rain 雨 | Rain 雨 | Rain 雨 | Rain 雨 | Sunny 晴 | Rain 雨 | Rain 雨 |
| Wind Power 风力 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 |

Arrival Schedule of Ships   船舶到港计划表

| Classification 类别 | Month 月份 | Name of goods 名称 | Name of vessel 船名 | Unloading Berth 卸船泊位 | Unloading Capacity 卸船量 | Pre Arrival Period 预到港期 |
| --- | --- | --- | --- | --- | --- | --- |
| 煤炭 | 10月 | 上旬煤炭 | MV TAURUS TWO | 8# | 45000 | 10月15日 |
|  |  | 中旬煤炭 | MV AFRICAN PUFFIN | 8# | 45000 | 计划10月30-11月3日 |
|  | 11月 | 中旬煤炭 | - | 8# | 45000 | 计划11月中旬 |
| 原油 | 10月 | Zakum原油 | MT COSWISDOM | 单点 | 130000 | 10月11日0800LT |
|  |  | Saharan Blend 原油 | MV Minerva Doxa | 单点 | 50000 | 10月26日-28日 |
|  | 11月 | CPC原油 | MT KASOS | 单点 | 130000 | 10月31日1000LT |
|  |  | QATAR MARINE原油 | - | 单点 | 130000 | 11月2日-12日 |
|  |  | SERIA原油 | - | 单点 | 80000 | 11月4日-5日 |
|  |  | MURBAN原油 | - | 单点 | 130000 | 11月14日-16日 |
|  | 12月 | 第1船SERIA原油 | - | 单点 | 80000 | 11月27日-12月3日 |
|  |  | 第2船Usan原油 | MT Amyntas | 单点 | 130000 | 12月1日-10日 |
|  |  | 第3船CPC原油 | - | 单点 | 130000 | 计划12月6日-8日 |
|  |  | 第4船FORCADOS原油 | - | 单点 | 130000 | 12月21日-22日 |
|  |  | 第5船ZAFIRO原油 | - | 单点 | 130000 | 12月15日-17日 |
|  |  | 第6船AGBAMI原油 | - | 单点 | 130000 | 12月21日-22日 |
| 石脑油 | 12月 | 重石脑油 | - | 4# | 22000 | 12月5日-10日 |
| 催化汽油 | 11月 | 催化汽油 | - | 4# | 35000 | 11月16日-20日 |
| 液化气 | 10月 | 第6船液化气 | MV PNX Conqueror | 4# | 2500 | 10月10日 |
| Remarks 备注 | 1、9月25日接收到12月份原油采购计划6船次73万吨； 2、9月27日落实11月重石脑油计划货量因供货商货量不足，调整为2.2万吨。 3、10月3日12月份原油计划原定12月8日进厂的 Akpo 原油取消，用 CPC 原油替代。数量 13 万吨，到港期12月8日。 4、11月3.5万吨汽油调和组分，原计划11月25日-30日到港，现调整为11月16日-20日； |  |  |  |  |  |

Statistics of Outsourcing Raw Materials (Unit: Tons)

外购原料统计（单位：吨）

| Product Number品号 | Incoming Volume进厂量 （卸货港商检量） | Usage Quantity 使用量 | Stock 当日库存 | Turnover Days 可周转天数 |
| --- | --- | --- | --- | --- |
| Crude Oil 原油 | 567973.673（17/5船） | 74120 | 502865 | - |
| Coal煤炭 | 265400（13/10船） | 1172 | 68365 | 45 |
| Catalytic Gasoline 汽油组分 | 19868.626（2/1船） | - | 19814 | - |
| Heavy Naphtha 重石脑油 | 19508.401（2/1船） | - | 19829 | - |
| LPG液化石油气 （剩余1船1次性开工物料） | 12465.830（6/5船） | 4424 | 8041 | - |
| 备注：计划采购生产物料4种34船，包含17船原油，已到港5船次567963吨，13船煤炭已到港10船次265400吨，2船汽油调和组分到港1船次19862吨，2船重石脑油到港1船次19508吨；另外开工一次性进厂开工物料计划采购6船LPG，剩余1船次0.24万吨未到港。 We plan to purchase 34 ships of 4 kinds of production materials, including 17 ships of crude oil, which has arrived at the port 5 ships of 567,963 tons, 13 ships of coal which has arrived at the port 10 ships of 265,400 tons, 2 ships of gasoline and mixed components which have arrived at the port 1 ship of 19862 tons, 2 ships of heavy naphtha which has arrived at the port 1 ship of 19,508 tons.In addition, 6 vessels of LPG are planned to be purchased in one time, and the remaining 1 vessel has not arrived at the port with 240,000 tons. |  |  |  |  |

Statistics of fly ash products (Unit: Tons)

粉煤灰产品统计（单位：吨）

| Product Number 品号 | Stock 库存（t） | yield 产量（t） | Daily sales 昨日销售量(t/车) | Weekly sales 本周销售(t/车) | Month sales 本月销售量(t/车) | Saleable Inventory 可销售库存（t） |
| --- | --- | --- | --- | --- | --- | --- |
| Ash 粉煤灰 | 100 | 70 | -/- | 40.94/4 | 40.94/4 | 100 |

生产及设备异常问题跟踪

| Department 部门 | Abnormal Production and Equipment Problems 生产及设备异常问题 |
| --- | --- |
| Wharf 码头 | - 单点获取3个月有效期LTO，有效期至2019年12月31日； SPM to obtain 3-month valid LTO, valid until December 31, 2019; 2、煤码头长期LTO有效期到2020年8月6日；煤码头升级9月20日已拿到，可靠泊DWT不超5.5万吨的船型; Long-term LTO for coal Jetty until 6/8/2020,3；Coal terminal upgrade has been obtained on September 20, and reliable berthing DWT does not exceed 55,000 tons of ship type. |
| Loading Station 装车站 | Gantry equipment and instruments have been installed, commissioning can be completed by the end of September, and the development of elevator system and ERP bridge system is under way. 公路出厂设备及仪表部分已完成安装，天梯系统与ERP联桥部分系统开发正在进行； |
| 备注：生产及设备异常问题跟踪：（调度日志中仅对码头、装车站影响销售的设备异常情况进行跟踪记录） Production and Equipment Abnormal Problem Tracking: (In the dispatching log, only the equipment abnormal situation affecting the sales of wharf and loading station is tracked and recorded) . |  |

Logistics dispatch information库存及船讯（10月7日06:00）

| 一、库存信息： |  |
| --- | --- |
| 1 | 截止10月7日06:00，煤炭库存68365吨，昨日消耗1172吨，下一船10月中旬煤炭4.5万吨，预计10月15日到港，到港后煤炭库存约为5.3万吨； As of 06:00 on October 6th, 68365 tons of coal were in stock, and 1172 tons were consumed yesterday. The next shipment of 45,000 tons of coal was expected to arrive at the port on October 15th. After arrival, the coal stock was about 53,000 tons. |
| 2 | 截止10月7日06:00，粉煤灰库存为100吨，6日无拉运计划，7日BHC计划拉运4车。 As of 06:00 on October 7th, the fly ash stock was 100 tons, and there was no pull plan on the 6th. On the 7th, BHC planned to pull 4 cars. |
| 二、船讯信息： |  |
| 1 | 10月上旬ZAKUM原油船“MT COSWISDOM LAKE”于9月18日完成装货，装货量共计26万吨（200万桶），于9月18日1000LT离开装货港驶往第一卸货港“新加坡”， 9月30日2200LT已抵达第一卸货港新加坡等待卸货，卸货量13万吨（100万桶），然后再驶往PMB卸货，卸货量13万吨（100万桶），预计抵达PMB时间为10月11日0800LT。海事局许可已经拿到，9月30日已获取能源局支持信函。保函问题落实后，进行报关。目前已经在第一卸货港新加坡锚地延误7天； In early October ZAKUM oil ship "MT COSWISDOM LAKE" on September 18, finish loading, the loading quantity is 260000 tons (2 million barrels), on September 18, 1000 lt from loading port to the first port of discharge "Singapore", September 30, 2200 lt has arrived in the port of discharge in Singapore waiting for unloading, amount of discharge 130000 tons (1 million barrels), and then to PMB, discharge amount of discharge 130000 tons (1 million barrels), is expected to arrive in PMB for October 11, 0800 lt.The maritime administration approval has been obtained, and the letter of support from the energy administration was received on September 30.After the guarantee problem is confirmed, the customs declaration shall be made.At present, it has been delayed for 7 days in Singapore anchorage, the first unloading port. |
| 2 | 10月下旬5万吨Saharan Blend 原油船舶“MT Minerva Doxa”于9月30日在装货港“Algeria ARZEW”完成装货作业并离泊，驶向第一卸货港“马来西亚”，预抵港时间为10月22日，然后再驶往PMB卸货，卸货量5万吨，预计抵达PMB时间为10月26-28日；10-12月剩余11船原油已一起申请进口许可。 In late October Saharn Blend crude oil ship "MT Minerva Doxa" on September 30 in the port of loading "Algeria ARZEW" finish loading operation and the navigation, the first port of discharge to "Malaysia", pre arrival time is on October 22nd, and then to PMB discharge, discharge capacity is 50000 tons, is expected to arrive in PMB for October 26-28;The remaining 11 ships of crude oil from October to December have applied for import license together. |
| 3 | 11月第1船13万吨CPC原油船“MT KASOS”于10月4日离开装货港“CPC Terminal”， 目前在博斯普鲁斯海峡入口等待通过，预计10月31日抵达PMB。In November, the 130,000-ton CPC crude oil ship “MT KASOS” left the loading port “CPC Terminal” on October 4, and is currently waiting at the entrance of the Bosphorus. It is expected to arrive at PMB on October 31. |
| 4 | 10月第二船LPG船“PNX CONQUEROR”目前驶往装货港越南 “Vung Tau”，预装货量2400吨，预计10月6日夜间抵达装货港,10月10日抵达PMB。 The second LPG vessel "PNX CONQUEROR" in October is currently heading for Vietnam's "Vung Tau" at the loading port, with a pre-loading capacity of 2400 tons. It is expected to arrive at the loading port on October 6 . Arrive at PMB on October 10th. |
| 5 | 10月中旬煤炭4.5万吨船舶“MV TAURUS TWO”目前驶往煤炭装货港印尼“Tanjung Bara”，预装货量4.5万吨，预计10月7日抵达装货港,10月15日抵达PMB. In mid-october, the ship "MV TAURUS TWO" with 45,000 tons of coal is now sailing to the coal loading port of Indonesia "Tanjung Bara", with a pre-loaded cargo volume of 45,000 tons. It is expected to arrive at the loading port on October 7. Arrive at PMB on October 15th. |