|  | 恒逸实业（文莱）有限公司 Hengyi Industries Sdn Bhd |  |  |
| --- | --- | --- | --- |
|  | 商务调运日报 Dispatcher Daily Report |  |  |
| Establishment Department 编制部门 |  | Commercial Department 商务部 | 18 October 2019 |

Weather Forecast

天气预测

| 18 October -24 October |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Weather天气 | Rain 雨 | Rain 雨 | Rain 雨 | Rain 雨 | Sunny 晴 | Rain 雨 | Rain 雨 |
| Wind Power 风力 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 | Level<3 |

Arrival Schedule of Ships

船舶到港计划表

| Classification 类别 | Month 月份 | Name of goods 名称 | Name of vessel 船名 | Unloading Berth 卸船泊位 | Unloading Capacity 卸船量 | Pre Arrival Period 预到港期 |
| --- | --- | --- | --- | --- | --- | --- |
| 煤炭 | 10月 | 上旬煤炭 | MV TAURUS TWO | 8# | 45000 | 10月14日1200LT（卸货中） |
|  |  | 中旬煤炭 | - | 8# | 45000 | 11月3日 |
|  | 11月 | 中旬煤炭 | - | 8# | 45000 | 计划11月25日 |
| 原油 | 10月 | Saharan Blend 原油 | MV Minerva Doxa | 单点 | 50000 | 10月29日0600LT |
|  | 11月 | CPC原油 | MT KASOS | 单点 | 130000 | 10月31日1000LT |
|  |  | QATAR MARINE原油+ ZAKUM原油 | MT SRI VISHNU | 单点 | 65000+65000 | 11月2日-12日 |
|  |  | SERIA原油 | - | 单点 | 80000 | 11月4日-5日 |
|  |  | MURBAN原油 | - | 单点 | 130000 | 11月23日-25日 |
|  | 12月 | 第1船SERIA原油 | - | 单点 | 80000 | 11月27日-12月3日 |
|  |  | 第2船Usan原油 | MT Amyntas | 单点 | 130000 | 12月4日-7日 |
|  |  | 第3船CPC原油 | - | 单点 | 130000 | 12月5日-12日 |
|  |  | 第5船ZAFIRO原油 | - | 单点 | 130000 | 12月5日 |
|  |  | 第4船FORCADOS原油 | NEW RESOURCE OR NEW CORAL 拼装 | 单点 | 130000 | 12月21日 |
|  |  | 第6船AGBAMI原油 |  | 单点 | 130000 | 12月21日 |
| 石脑油 | 12月 | 重石脑油 | - | 4# | 22000 | 12月7日-11日 |
| 催化汽油 | 11月 | 催化汽油 | - | 4# | 35000 | 11月16日-20日 |
| Remarks 备注 | 1、9月25日接收到12月份原油采购计划6船次73万吨； 2、9月27日落实11月重石脑油计划货量因供货商货量不足，调整为2.2万吨。10月7日意向采购俄罗斯重石，采购货量预计在3-3.3万吨。 3、10月3日12月份原油计划原定12月8日进厂的 Akpo 原油用 CPC 原油替代。数量 13 万吨，到港期12月5日-12日。 4、11月3.5万吨汽油调和组分，原计划11月25日-30日到港，现调整为11月16日-20日； |  |  |  |  |  |

生产及设备异常问题跟踪

| Department 部门 | Abnormal Production and Equipment Problems 生产及设备异常问题 |
| --- | --- |
| Wharf 码头 | - 单点获取3个月有效期LTO，有效期至2019年12月31日； SPM to obtain 3-month valid LTO, valid until December 31, 2019; 2、煤码头长期LTO有效期到2020年8月6日；煤码头升级9月20日已拿到，可靠泊DWT不超5.5万吨的船型; Long-term LTO for coal Jetty until 6/8/2020,3；Coal terminal upgrade has been obtained on September 20, and reliable berthing DWT does not exceed 55,000 tons of ship type. |
| Loading Station 装车站 | Gantry equipment and instruments have been installed, commissioning can be completed by the end of September, and the development of elevator system and ERP bridge system is under way. 公路出厂设备及仪表部分已完成安装，天梯系统与ERP联桥部分系统开发正在进行； |
| 备注：生产及设备异常问题跟踪：（调度日志中仅对码头、装车站影响销售的设备异常情况进行跟踪记录） Production and Equipment Abnormal Problem Tracking: (In the dispatching log, only the equipment abnormal situation affecting the sales of wharf and loading station is tracked and recorded) . |  |

Logistics dispatch information库存及船讯

（10月18日06:00）

| 一、库存信息： |  |
| --- | --- |
| 1 | 截止10月18日06:00，煤炭库存84606吨，昨日消耗2834吨，卸货入库9605吨，预计完成卸货后库存为8.7万吨。 As of 06:00 on October 18, coal inventory was 84,606 tons, and 2,834 tons were consumed yesterday. 9,605 tons were discharged and put into storage. It is estimated that the inventory will be 87,000 tons after unloading. |
| 2 | 截止10月18日06:00，原油库存64.8万吨，昨日消耗0吨. As of 06:00 oct.18, crude oil inventory was 648,000 tons, which consumed 0 tons yesterday. |
| 3 | 截止10月18日06:00，粉煤灰库存为170吨，昨日粉煤灰出厂2车20.94吨，本月出厂389.36吨，完成计划的49%。今日计划RMC拉运3车、BHC拉运1车。 As of 06:00 on October 18th, the inventory of fly ash is 170 tons. Yesterday, the factory delivered 20.94 tons of fly ash for 2 vehicles, and 389.36 tons for this month, 49% percent of the planned.It is planned that RMC will transport 3 cars and BHC will transport 1 car today. |
| 二、船讯信息： |  |
| 1 | 煤炭船“MV TAURUS TWO” 于14日1200LT抵达PMB，并于14日1834LT开始卸货，截止18日0600LT累计卸货4万吨，平均卸货速率500吨/小时；剩余5000吨，预计10月18日下午卸货完成。 The coal ship "MV TAURUS TWO" arrived at PMB on 14th, 1200LT, and started unloading on 14th, 1834LT. By 18th, 0600LT accumulated 40,000 tons of unloading, and the average unloading rate was 500 tons/hour.The remaining 5,000 tons is expected to be discharged in the afternoon of October 18. |
| 2 | 10月下旬5万吨Saharan Blend 原油船舶“MT Minerva Doxa”于9月30日在装货港“Algeria ARZEW”完成装货并离泊，驶向第一卸货港“马来西亚”，预抵港时间为10月23日，然后再驶往PMB卸货，卸货量5万吨，预计抵达PMB时间为10月29日0600LT。10月-12月剩余11船原油已一起申请进口许可预计本周收到。 In late October, MT Minerva Doxa, a 50,000-ton Saharan Blend crude oil ship, finished loading and leaving the dock at the loading port "Algeria ARZEW" on September 30, and sailed to the first unloading port "Malaysia". The pre-arrival time is October 23, and then it sailed to PMB for unloading. The unloading volume is 50,000 tons, and the expected arrival time of PMB is October 29, 0600LT.The remaining 11 shipments of crude oil from October to December have applied for import license together, which is expected to be received this week. |
| 3 | 11月第1船13万吨CPC原油船“MT KASOS”于10月4日离开装货港“CPC Terminal”开往PMB，预计10月31日1000LT抵达PMB。 The first 130,000 tons CPC crude oil tanker MT KASOS left the loading port "CPC Terminal" for PMB on October 4 and is expected to arrive at PMB at 1000LT on October 31. |